{"text_format":"2","workbook":"xlsx","n_sheets":8,"sheets":["專案結案統計表","工作彙報時間統計表(彙總)","工作彙報時間統計表(明細)","時間分布統計表","待辦事項列表(已完成)","SD列印(已完成)","需求變更單列印(已完成)","專案任務進度表(已完成)"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":3,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"專案結案統計表","index":0,"n_rows":12,"n_cols":9,"rows_kept":12,"cut":false,"hidden":false,"merged":[[11,0,11,1]]}
[]
["專案名稱：","台灣文創ERP案",null,"專案經理","蓋冠宇、趙曉杰"]
["預計啟始日期","2013-02-01",null,"實際啟始日期","2013-02-15",null,"時間差異",{"$f":"E3-B3","v":14},"日"]
["預計結束日期","2014-03-01",null,"實際結束日期","2015-02-01",null,"時間差異",{"$f":"E4-B4","v":337},"日"]
[]
["程式支數",200,"支","需求變動次數",80,"次","程式異動率",{"$f":"E6/B6","v":0.4}]
["參與人員","專案角色","負責程式","任務達成率","平均開發時間","程式錯誤數","平均修復時間","程式錯誤率"]
["蓋冠宇","專案經理",0,0,0,0,0,0]
["陳洪濤","專案經理/\n系統分析師/\n程式設計師",80,0.7,13.5,30,4.3,{"$f":"F9/C9","v":0.375}]
["張麗娜","程式設計師",80,0.65,16,35,5,{"$f":"F10/C10","v":0.4375}]
["趙曉傑","程式設計師",40,0.4,21.3,13,8,0.32500000000000001]
["成效總計",null,{"$f":"SUM(C8:C11)","v":200},{"$f":"SUM(D8:D11)/4","v":0.4375},{"$f":"SUM(E8:E11)/4","v":12.7},{"$f":"SUM(F8:F11)","v":78},{"$f":"SUM(G8:G11)/4","v":4.3250000000000002},{"$f":"SUM(H8:H11)/4","v":0.28437499999999999}]

{"sheet":"工作彙報時間統計表(彙總)","index":1,"n_rows":13,"n_cols":11,"rows_kept":13,"cut":false,"hidden":false,"merged":[[8,0,8,3],[3,2,3,3],[4,2,4,3],[5,2,5,3],[6,2,6,3],[7,2,7,3]]}
[]
["統計時間起","2015-01-01",null,"統計時間迄","2015-01-31",null,"列表日期","2015-02-28",null,"製表人","蓋冠宇"]
[]
["序號","人員名稱","專案名稱",null,"專案工作","需求變更","修正錯誤","系統優化","日常工作","業務工作","備註"]
[1,"蓋冠宇","文創ERP案",null,30,20,5,0,10,25.5]
[2,"蓋冠宇","盛群半導體Portal案",null,35.5,23.5,10,5,15,15]
[3,"陳洪濤","文創ERP案",null,50.5,20,30,15,5,0]
[4,"張麗娜","文創ERP案",null,23,25,30,15,10,0]
["總計",null,null,null,{"$f":"SUM(E5:E8)","v":139},{"$f":"SUM(F5:F8)","v":88.5},75,35,40,40.5]
[]
[]
[null,null,null,"選擇條件"]
[null,null,null,"複選條件"]

{"sheet":"工作彙報時間統計表(明細)","index":2,"n_rows":23,"n_cols":13,"rows_kept":23,"cut":false,"hidden":false,"merged":[[2,7,2,10],[4,4,4,6],[5,4,5,6],[5,2,5,3],[12,4,12,6],[7,2,7,3],[8,2,8,3],[7,4,7,6],[8,4,8,6],[2,1,2,2],[6,2,6,3],[6,4,6,6],[13,4,13,6],[14,4,14,6],[9,4,9,6],[10,4,10,6],[11,4,11,6],[20,2,20,3],[15,4,15,6],[16,4,16,6],[17,4,17,6],[16,2,16,3],[17,2,17,3],[21,2,21,3],[22,0,22,6],[21,4,21,6],[4,2,4,3],[9,2,9,3],[10,2,10,3],[11,2,11,3],[12,2,12,3],[13,2,13,3],[14,2,14,3],[15,2,15,3],[18,4,18,6],[19,4,19,6],[20,4,20,6],[18,2,18,3],[19,2,19,3]]}
[]
["統計時間：","2015-01-01","~","2015-01-31",null,null,"列表日期：","2015-02-28",null,"製表人：","蓋冠宇"]
["專案名稱：","文創ERP案",{"$nulls":4},"專案成員：","蓋冠宇"]
[]
["序號","日期","時間區間",null,"工作內容",null,null,"專案工作","需求變更","修正錯誤","系統優化","日常工作","業務工作"]
[1,"2015-01-01","09:30~12:00",null,"測試工作",{"$nulls":4},2.5]
[2,"2015-01-01","13:00~14:00",null,"程式開發",null,null,1]
[3,"2015-01-02","09:00~12:00",null,"程式開發",null,null,3]
[4,"2015-01-02","13:00~18:00",null,"程式開發",null,null,null,5]
[5,"2015-01-04","10:00~11:30",null,"程式開發",null,null,1.5]
[6,"2015-01-05"]
[7,"2015-01-06"]
[8,"2015-01-07"]
[9,"2015-01-08"]
[10,"2015-01-09"]
[11,"2015-01-10"]
[12,"2015-01-11"]
[13,"2015-01-12"]
[14,"2015-01-13"]
[15,"2015-01-14"]
[16,"2015-01-15"]
[17,"2015-01-16"]
["總計",{"$nulls":6},{"$f":"SUM(H6:H22)","v":5.5},{"$f":"SUM(I6:I22)","v":5},{"$f":"SUM(J6:J22)","v":2.5},0,0,0]

{"sheet":"時間分布統計表","index":3,"n_rows":13,"n_cols":11,"rows_kept":13,"cut":false,"hidden":false,"merged":[[3,0,5,0],[3,1,5,1],[6,0,8,0],[6,1,8,1],[9,1,12,1],[9,0,12,0]]}
["統計時間起","2015-01-01",null,"統計時間迄","2015-01-31",null,"列表日期","2015-02-28",null,"製表人","蓋冠宇"]
[]
["項次","專案名稱","成員名稱","工作時數","所佔比率"]
[1,"百威人力委外案","張居富(Dean)",80,{"$f":"D4/(D4+D7+D13)","v":0.5161290322580645}]
[null,null,"廖人頡(Gary)",130,{"$f":"D5/(D5+D8)","v":0.8125}]
[null,null,"鄭哲宇(Ted)",150,1]
[2,"山富航空自由行案","張居富(Dean)",70,{"$f":"D7/(D4+D7+D13)","v":0.45161290322580644}]
[null,null,"廖人頡(Gary)",30,{"$f":"D8/(D5+D8)","v":0.1875}]
[null,null,"張麗娜(Alina)",60,{"$f":"D9/(D9+D12)","v":0.375}]
[3,"台灣文創人力委外案","蓋冠宇(Nelson)",0,0]
[null,null,"陳洪濤(Ethan)",60,{"$f":"D11/160","v":0.375}]
[null,null,"張麗娜(Alina)",100,{"$f":"D12/(D9+D12)","v":0.625}]
[null,null,"張居富(Dean)",5,{"$f":"D13/(D4+D7+D13)","v":3.2258064516129031E-2}]

{"sheet":"待辦事項列表(已完成)","index":4,"n_rows":7,"n_cols":8,"rows_kept":7,"cut":false,"hidden":false,"merged":[[1,6,1,7],[0,0,0,7]]}
["待辦事項列表"]
[{"$nulls":6},"列表日期：2015/3/20  10:30:00"]
["項目編號","事件所有人","待辦事項主旨","重要性","狀態","完成度","指派人","待辦說明"]
[1,"蓋冠宇","有關於個人化首頁的規範設定","普通","進行中",0.5,"蓋冠宇","Dear Ted,\n    請將個人化首頁撰寫的工作規範記錄在程式記錄討論區中!"]
[2,"蓋冠宇","思考不同專案，如何合併在專案任務管理功能中","普通","進行中",0.3,"蓋冠宇","因為不同的專案，會有不同的任務，如果將專案工作項目加入呈現條件中，預設為空值時，就會產生過多的欄位，反而不好閱讀。"]
[3,"原玉東","請將管理系統的程式及資料補到正式機","普通","進行中",0.3,"蓋冠宇","Dear John,\n請將我們管理系統所撰寫的程式、資料表、及各項資料，以本系統專案管理的方式進行填寫!\n我會將你指派為這個專案的專案經理，我們共同以專案管理的角度檢視開發到目前為止，是否順暢。"]
[4,"…"]

{"sheet":"SD列印(已完成)","index":5,"n_rows":3,"n_cols":1,"rows_kept":3,"cut":false,"hidden":false,"merged":[]}
["1.應匯出成PDF、Word等格式"]
["2. 以每章節為一支程式的SD附加累次的需求變更產生檔案。"]
["3. 因為檔案可能很大，所以要考慮效能及做法上(例如：每次產生一個模組)。"]

{"sheet":"需求變更單列印(已完成)","index":6,"n_rows":1,"n_cols":1,"rows_kept":1,"cut":false,"hidden":false,"merged":[]}
["1. 每次印出一個需求的需求變更單。"]

{"sheet":"專案任務進度表(已完成)","index":7,"n_rows":12,"n_cols":14,"rows_kept":12,"cut":false,"hidden":false,"merged":[[1,0,1,13],[0,0,0,13]]}
["專案任務進度表"]
["匯出時間:2015/03/20"]
["項次","專案名稱","模組名稱","程式名稱","專案管理","需求訪談","系統分析","系統設計","開發環境準備","程式撰寫","單元測試","整合性測試","壓力測試","程式上線"]
[1,"ANS系統改寫案","[2]基本物料資訊查詢","1. 供應商基本資料查詢（V.1）",null,null,null,1,null,1]
[2,"ANS系統改寫案","[2]基本物料資訊查詢","2. 生產品號基本資料查詢（V.1）",null,null,null,1,null,1]
[3,"ANS系統改寫案","[2]基本物料資訊查詢","3. 廠商交貨車輛管制查詢（V.1）",null,null,null,1,null,1]
[4,"ANS系統改寫案","[2]基本物料資訊查詢","X. 使用手冊（V.1）",null,null,null,1,null,1]
[5,"ANS系統改寫案","[3]日常物料資訊查詢","1. 廠商交貨作業（V.1）",null,null,null,1,null,1]
[6,"ANS系統改寫案","[3]日常物料資訊查詢","10. 異常登入報表（V.1）",null,null,null,1,null,1]
[7,"ANS系統改寫案","[3]日常物料資訊查詢","11. 廠商密碼重設流程（V.1）",null,null,null,1,null,1]
[8,"ANS系統改寫案","[3]日常物料資訊查詢","2. 發票明細查詢（V.1）",null,null,null,1,null,1]
[9,"ANS系統改寫案","[3]日常物料資訊查詢","3. 發票總額查詢（V.1）",null,null,null,1,null,1]